## Readiness checker
LPA name: | Ipswich Borough Council
Version number: | 1
Date: | 2026-10-26
Lead officer | James Mann
Area | Activity | We have made the recommended progress |  | We have started but have a bit more work to do to make the recommended progress |  | We may not have started or have significant work to do to make the recommended progress |  | Notes
Legal requirements you must have met before proceeding | Preparing and publishing a timetable in line with the data standard, publishing a notice of intention to commence and undertaking the scoping consultation | TRUE | We have complied with these legal requirements. | FALSE |  | FALSE | We have not met some or all of these legal requirements. | The Council prepared and published its Local Plan Timetable, in accordance with the data standard, and Notice of Intention to Commence Local Plan Preparation on 25 June 2026. The Council commenced its Local Plan Scoping Consultation on 8 July. The consultation ran for 8-weeks closing on 2 September 2026. A Strategic Environmental Assessment scoping consultation has been undertaken on the same dates. The Council has therefore published the required notice and timetable and undertaken the statutory scoping consultation in accordance with the legal requirements.
Preparing and publishing a local plan timetable | Considering the expected time it will take to adopt the plan | FALSE | The timetable shows how we will prepare and adopt a plan within 30 months. | TRUE | The timetable shows how we will prepare and adopt a plan within 30 months but there are significant risks to this. | FALSE | The timetable shows that preparing and adopting a plan will take substantially longer than 30 months. | The Council has prepared and published a Local Plan timetable setting out the key stages and anticipated dates for adopting the new Local Plan. The timetable shows how we will prepare and adopt the plan within 30-months but there are significant risks to this. The Local Plan Project Initiation Document (PID) has identified the key risks and process to address them. Progress will be monitored through plan preparation and the timetable reviewed where necessary.
Establishing project management and governance arrangements | Establishing appropriate project management, governance and resourcing to support the timetable | TRUE | We have a robust approach to manage, govern, resource and finance the preparation of the plan that supports the delivery of the local plan timetable. | FALSE | We have considered our approach to manage, govern, resource and finance the preparation of the plan, but there are some gaps or an approach is not yet signed off. | FALSE | We have key unresolved questions for how we willl manage, govern, resource or finance the preparation of the plan. | The Council has prepared a PID which provides the overarching project management framework for the preparation of the Local Plan. The PID brings together the proposed project management arrangements, governance and decision-making routes, Local Plan programme, resource requirements and budget considerations. These have been considered against the timetable for preparing the Local Plan to identify the resources and arrangements required to support delivery.
| Testing and agreeing project management and governance internally | TRUE | All relevant teams and decision makers have been involved in designing, and signing-off the approach. | FALSE | Relevant teams and decisions makers have been involved in designing and testing our approach, but it is not yet signed off. | FALSE | We still need to involve other relevant teams and decision makers. | The proposed project management and governance arrangements have been developed in consultation with relevant officers and decision-makers across the Council. The Local Plan PID brings these arrangements together including setting out roles and responsibilities, project management arrangements, governance and decision-making routes.
| Establishing risk monitoring, management and mitigation | TRUE | We have identified potential risks and have effective processes in place to monitor, manage and mitigate them. | FALSE | We have identified potential risks and are working to establish processes to monitor, manage and mitigate them. | FALSE | We're still identifying risks or are yet to consider how we will monitor, manage and mitigate them. | Key risks have been embedded within the Local Plan PID. This identifies the risks associated with preparation of the Local Plan and sets out the proposed approach to their management and mitigation. The identified risks will be reviewed throughout the plan-making process and the risks updated accordingly to reflect changes in circumstances, emerging risks and any additional mitigation required.
Consulting and engaging on the plan | Preparing an engagement strategy | TRUE | We have a positive strategy for engaging the community and other key stakeholders in the preparation of the plan, which has been prepared with regard to government guidance. | FALSE | We have made some progress in preparing an engagement strategy. | FALSE | We need to start preparing an engagement strategy. | The Council has prepared an Engagement Strategy for the new Local Plan, having regard to relevant government guidance and relevant Council strategies and guidance. It establishes a clear and proportionate framework for engagement throughout the plan-making process. The Engagement Strategy has been informed by feedback received through the Scoping Consultation and responds to Ipswich’s demographic profile, and has been developed with advice and guidance from the Council’s Communities, Information Governance and Legal teams.
| Establishing processes for consultation and engagement | TRUE | We have clear processes in place to maximise diversity in participation, utilising both digital-first and traditional methods. | FALSE | We have scoped out digital-first and traditional methods for engaging with different audiences, but our processes are not yet fully formed. | FALSE | We haven't explored what engagement methods we could use. | The Engagement Strategy sets out a digital-first approach, complemented by traditional and non-digital methods to provide different ways for people to participate. The approach has been informed by Ipswich’s demographic profile and feedback from the Scoping Consultation, including consideration of groups that may experience barriers to engagement.
| Agreeing the engagement strategy internally | TRUE | We have sought feedback on and agreed the engagement strategy with key decision makers. |  | We have sought feedback on the engagement strategy with key decision makers, but it's not yet signed off. | FALSE | We still need to seek feedback on our engagement approach with key decision makers. | As delegated by Executive through decision E/26/02 the Engagement Strategy has been formally approved by the Head of Planning and Economic Development, in consultation with the Portfolio Holder for Planning and Museums and Executive Director for Place, Operations and Communities.
Scoping the anticipated content of the plan | Defining the scope of the plan | TRUE | We understand the proposed scope of the local plan. We know the main areas or locally specific subject matters it will address. This is based on data from the existing local plan, as well as information gathering, baselining and early engagement to date. Scoping work aligns with the work we have carried out on our SEA (if SEA is required). | FALSE | Scoping work is underway. We have reviewed monitoring information for the previous local plan, but still have work to do on information gathering, baselining and early engagement. The scoping work aligns or partially aligns with the work we have carried out on our SEA (if SEA is required). | FALSE | We're only in the early stages of scoping and haven’t considered how this relates to the SEA. | This is set out in the PID. Locally specific issues and priorities have been identified through the Local Plan Scoping Consultation, together with targeted engagement with underrepresented groups undertaken during summer 2025. This has provided a strong understanding of the matters that are important to Ipswich’s communities. The Council publishes an Authority Monitoring Report each year which tracks progress against the objectives and policies of the adopted Local Plan. This Local Plan monitoring and the early baseline evidence has been used to identify areas where progress has been sustained and where performance has remained static or declined, enabling the new Local Plan to respond to identified delivery challenges. The Council has also commissioned an independent Strategic Environmental Assessment (SEA). The SEA Scoping Report and associated consultation establish the environmental, social and economic baseline, identify key sustainability issues and will inform and refine the scope of the plan. The scope will also reflect the Council’s priorities as set out in the Corporate Strategy, alongside national policy and government priorities. Together, the PID, early baseline evidence, monitoring evidence, community engagement and SEA process provide a clear and robust basis for defining the scope of the new Local Plan.
| Drafting a vision for the plan | FALSE | We have used early baselining and engagement activities to begin drafting a vision. | TRUE | Using our baselining work and analysis of feedback from the scoping consultation we have started to develop some ideas about what the vision might focus on. | FALSE | We need to start drafting a vision. | The Council has used early baseline evidence and engagement activities to begin developing a draft vision for the new Local Plan. This has included consideration of the key characteristics, issues and opportunities identified through the Council’s baselining work, feedback received through the Local Plan Scoping Consultation, and recent town centre themed engagement events. This work provides the starting point for developing the Local Plan vision, which will be refined as plan preparation progresses and further evidence and engagement are undertaken.
| Considering how we will monitor progress towards the vision | FALSE | We have started to identify measurable outcomes to monitor our progress towards the vision. | TRUE | We have considered how we might monitor progress towards our vision, but haven’t identified specific measurable outcomes yet. | FALSE | We haven’t considered how we will monitor progress towards our vision. | The Council has begun to consider how progress towards the emerging Local Plan vision will be monitored, although specific measurable outcomes and indicators have not yet been identified.
| Gathering evidence to inform the new plan | TRUE | We have mostly identified and scoped our evidence needs and have a plan for how we will deliver this. | FALSE | We have identified some of our evidence needs but still have work to do to scope the work and identify how we will deliver this. | FALSE | We need to start identifying our evidence needs and how we will deliver this. | The Council has identified the evidence required to support preparation of the new Local Plan through the PID. This establishes a clear and coordinated evidence programme covering the principal matters that will inform the new plan. A number of studies have been commissioned and are underway, while project briefs have been prepared for evidence base studies to progress in accordance with the Local Plan timetable. The Councils specific studies include evidence on future retail needs, land supply, heritage and conservation and environmental assessment. Several strategic evidence-base studies have been commissioned on a joint basis with other Suffolk local planning authorities. This approach provides a consistent evidence base across Suffolk and supports the effective consideration of strategic matters and cross-boundary matters. These joint studies include evidence on future housing and economic needs (including Gypsy and Traveller Accommodation Needs), water resources and transport assessment.
| Calculating a housing requirement | TRUE | We have calculated a housing requirement for the plan area using the Government's recommended standard method and started to identify the needs for homes of different sizes, types and tenures, including affordable homes. | FALSE | We have calculated a housing requirement for the plan area using the Government's standard method. We haven't started to identify the need for homes of different sizes, types and tenures and affordable homes yet. | FALSE | We haven’t calculated a housing requirement using the Government’s standard method. | he housing requirement for Ipswich has been calculated at 715 dwellings per annum, using the Government’s standard method. This provides the starting point for preparing the new Local Plan, and the calculation will be kept under review while the plan is developed. Work on a Housing Needs Assessment has commenced. This will identify the need for homes of different sizes, types and tenures, including affordable housing, to be accommodated over the plan period.
| Exploring our high-level options and policies | FALSE | We have started to consider high-level and conceptual spatial options to deliver the identified development need, and begun to identify the potential scope of locally specific policies. | TRUE | We have identified the high-level capacity and constraints for development but have not started to develop spatial options to deliver the development need or scoped out locally specific policies | FALSE | We haven’t done any work on high-level spatial options or locally specific policies. | The Scoping Consultation has provided an early opportunity to identify issues, opportunities and priorities for the Borough and to inform the spatial and policy choices that will be explored as plan preparations progress.
Progressing the Strategic Environmental Assessment | Identifying other plans/programmes that have a relationship with the local plan | TRUE | We have identified other relevant plans and programmes and their relationship to the local plan to establish how the plan or programme is affected by those plans or programmes. | FALSE | We have identified other relevant plans and programmes but have not yet analysed how the local plan is affected by those plans or programmes. | FALSE | We have not yet identified other relevant plans or programmes that affect the local plan. | The Scoping Report reviews the international, national and sub-national plans, policies and programmes relevant to the new Local Plan. It identifies their relationship with the plan and incorporates their objectives and requirements into the SEA framework.
| Collecting baseline information for the SEA | TRUE | We have identified baseline information showing the existing environmental characteristics of the area and their likely evolution without implementation of a new plan, as well as data on historic and likely future trends. It provides the basis against which we can assess the likely effects of our different options. | FALSE | We have identified baseline information on the existing environmental characteristics of the area. We have not used this information to establish trends or used it to test the environmental effects of our options. | FALSE | We are in the early stages of (or haven’t yet started) assembling baseline information to inform our strategic environmental assessment. | A comprehensive baseline has been assembled covering biodiversity, population, human health, soils, water, air quality, climate change, material assets, cultural heritage, landscape and townscape. The report identifies current conditions, key trends, data limitations and the likely evolution of these matters without the new Local Plan.
| Identify environmental protection objectives to inform plan preparation | TRUE | We have identified the relevant environmental protection objectives, established at international, community or national level, and environmental considerations that will be taken into account during the preparation of the plan and recorded in the environmental report. | FALSE | We are in the process of identifying relevant environmental protection objectives that will be taken into account when preparing the plan. | FALSE | We have not identified any environmental protection objectives. | Relevant environmental protection objectives have been identified through the review of legislation and other plans and programmes. These objectives have directly informed the SEA framework and will ensure that environmental considerations are integrated into the preparation of the Local Plan.
| Developing the scope of the SEA | TRUE | We have begun to identify the scope and level of detail of the information we intend to include in the environmental report. We have started to set out this information in a suitable document, such as a draft, emerging environmental report or scoping document. We are on track to consult on the scope of the SEA at the consultation on proposed plan content and evidence. | FALSE | We’re still working out what the scope and/or level of detail to include in the environmental report. We’re making progress on setting out this information in an appropriate document, but we’re not ready to consult on the scope of the SEA. | FALSE | We have not decided on the scope of the SEA or the level of detail we should include in the environmental report. | The Scoping Report establishes the context, geographical coverage, key sustainability issues, assessment framework and proposed methodology for the SEA. Consultation with the Environment Agency, Historic England, Natural England and other stakeholders provides an opportunity to confirm and refine the scope before the assessment of reasonable alternatives and emerging plan content begins.
| Developing SEA objectives | TRUE | We have started to develop SEA objectives which will help assess the environmental performance of the local plan. | FALSE | We have begun to identify the key themes likely to be important when developing SEA objectives to use to assess the environmental performance of the local plan. | FALSE | We have not yet begun on developing SEA objectives to assess the environmenta performance of the plan against. | The Council has established 11 SEA objectives covering biodiversity and geodiversity; housing; health and health inequalities; soils and minerals; water; air quality; climate change; prosperity and growth; heritage; landscape and townscape; and waste management. Supporting appraisal questions have also been developed to provide a clear and consistent framework for assessing the Local Plan’s spatial options, sites and policies.